## Editor Issues
ID | Title | Description | Reported by | Priority | Issue Status | Assigned To | Estimation | Comment
1 | Structuring editors with the help of packages | Some editors are related with packages. This misuses the package structure. Henrik Lönn:What about this: Packages contain packaeble elements Diagrams only show and add elements according to their purpose (VFM, AF, DF, HW, Allocation, etc.) Diagrams have a “home” package in which all elements are created when added to the Canvas (this is shown on its properties, and changeable in the package structure) Diagrams can show elements from other packages, depending on diagram type (e.g. requirements can be shown with a feature, regardless of package containment) A diagram navigator is shown, where the package structure is mimicked and diagrams shown. Package path is shown on diagram’s advanced tab Package path is shown on elements’ advanced tab Owning Element’s name is shown on tab for diagrams, instead of diagram type Diagram type and owning element is shown in Properties window when selecting the canvas= no element | Henrik Lönn | Medium | New
2 | Use properties view from Eclipse | Henrik Lönn: Selecting an element in the diagram shows property view from tree viewer (richer than the diagram’s property window) | Henrik Lönn | High | New
3 | Show properties of connectors | Selecting connector should show connector properties. This is not always the case. | Stefan Voget | High | New
4 | Copy and paste in diagram | Enable a copy and paste of elements in diagrams. | Henrik Lönn | Low | New
5 | Pull packages and or elements. | It should be possible to pull packages from the tree onto the canvas. | Henrik Lönn | Low | Rejected |  |  | This feature is against the editor philosophy. The editors are combined with packages, i.e. each editor defines a new package and contains subpackages only
6 | Drag and drop of ports | It is a non documented function, that ports can be added by drag and drop in the Analysis Function Type Package diagram. Ports can be pulled twice from tree onto a prototype Ports can be pulled onto the wrong prototype, in which case they are moved in the tree Port names are duplicated when adding a type to prototype in AFTdiagram | Henrik Lönn | High | New
7 | Drag and drop of packages and types | It is a non documented function, that packages and types can be added by drag and drop in the Analysis Function Type Package diagram. | Henrik Lönn | High | New
8 | Two menues in the palette. | Two menues with same content occur: Modeling and Objects | Henrik Lönn | Medium | New
9 | small and big letters | Small and big letters in "*Package"-classes have to be corrected. Actual: SystemmodelingPackage, FunctionmodelingPackage, etc. Former: SystemModelingPackage, FunctionModelingPackage, etc. same for _instanceRef packages: Actual: _instanceref, _instancerefFactory Former: _instanceRef, instanceRefFactory | Mark-Oliver Reiser | Medium | New
10 | Sphinx bug No. 409152 | Due to Sphinx bug No. 409152 two files have to be replaced. They are available in the download area of the Eclipse lab | Stefan Voget | High | New
11 | Sphinx bug No. 409411 | Due to Sphinx bug No. 409411 a patch has to be used. It is available in the download area of the Eclipse lab | Stefan Voget | High | New
12 | Do not double click before safe. | If you create an element on a diagram and change the diagram before safe, the element is not connected to an associated business object. The synchronization between element on the diagram and the element in the model is not given. The element has to be deleted first before continuing. | Stefan Voget | High | Assigned | Martin Lang
13 | Dublications in EMTD | All elements which can be created via the palette on this diagram can also be selected in the model browser and drag&dropped. This selection feature is not specified and shall be removed. | Stefan Voget | Medium | Assigned | Martin Lang
14 | Environment Diagram not specified well | The specification of the editor has to be updated, as an environment model cannot be a part of a type at the same time | Stefan Voget | High | DONE
15 | One safety Constraint too much | In case a safety constraint package is added in the ED diagram, in addition a safety constraint is added. This safety constraint has not to be added | Stefan Voget | Medium | DONE
16 | Missing relationship in safety constraint diagram | If one tries to draw a safety constraint to fault failure association, this is not added in the model. | Stefan Voget | Medium | DONE
17 | Missing relationship in EMT diagram | If one tries to draw a errorBehavior to InternalFaultProt. Or ProcessFaultProt., this is not possible. | Stefan Voget | Medium | DONE
18 | EMT Diagram with wrong association | EAST-ADL specification the role name or the internalFailure role of the association between ErrorBehavior is not set. | Stefan Voget | Medium | DONE
19 | Demonstrator | A demonstrator of the editor is needed. Create an exe. | Stefan Voget | High | Assigned | Martin Lang
20 | Architecture documentation | In form of cheat sheets: - How to implement an editor - How to implement properties view - How to synchronize model with editor - Specific topics in more detail (instanceRefs, Type/Prototype, Ports, derivation of ports, ...) | Stefan Voget | High | Assigned | Martin Lang
21 | "Save all" bug | Eatop 2.1.12 + Sphinx version 0.7.0: Using the "Save All Button" will make all unsaved elements dirty. | Martin Lang | Medium | New
22 | Unify Features | Many features have to be unified because every developer prefered his own structure while programmming. Especially: Delete Features, Instancerefs, Connection Features, …) | Martin Lang | High | Assigned | Martin Lang